## Sheet1
Number | Task | Estimated Duration for each task | Actual Finish | Time (Actual day) | Planned Progress | Actual Progress
1.1 | Team Allocation | 1 | 1 | 0 | 0 | 0
1.2 | Finalising Problem Statement | 1 | 2 | 2 | 2.0667 | 1
1.3 | Sprint Planning | 1 | 3 | 4 | 4.1333 | 3
1.4 | Project Management Tool SetUp | 1 | 4 | 6 | 6.2 | 4
2.1 | Elicitation | 3 | 7 | 8 | 8.2667 | 7
2.2 | Determine Functional and Non Functional features | 1 | 10 | 10 | 10.3333 | 7
2.3 | Design Work Breakdown Structure | 3 | 15 | 12 | 12.4 | 8
3.1 | Design UML Use Case Diagram | 5 | 20 | 14 | 14.4667 | 8
3.2 | Design UML State Diagram | 3 | 20 | 16 | 16.5333 | 11
3.3 | Design UML Sequence Diagram | 5 | 22 | 18 | 18.6 | 11
3.4 | Design UML Activity Diagram | 3 | 25 | 20 | 20.6667 | 11
4.1 | Draft the Report | 3 | 28 | 22 | 22.7333 | 19
4.2 | Finalise the Report | 1 | 30 | 24 | 24.8 | 24
|  |  |  | 26 | 26.8667 | 27
|  |  |  | 28 | 28.9333 | 27
| Sum Of Task Duration | 31 |  | 30 | 31 | 30
| Planned Project Duration | 30
| Planned Progress per Day | 1.0333